## Plan template
Website migration plan
Save a copy of this workbook. Fill amber inputs with actual owners, dates and evidence. Pass means a completed check.
Project
Release owner
Planned launch
Launch decision | Enter project, owner and launch date
Baseline evidence
ID | Measure | Scope or URL | Period or method | Evidence reference | Owner | Captured on | Result | Limits or notes
B01 | URL and redirect inventory | [5 empty] | Not checked
B02 | Search Console export | [5 empty] | Not checked
B03 | Enquiry/order baseline | [5 empty] | Not checked
B04 | Representative speed test | [5 empty] | Not checked
B05 | Platform and account inventory | [5 empty] | Not checked
B06 | Recovery point and restore test | [5 empty] | Not checked
Task register
ID | Task and acceptance | Owner | Depends on IDs | Deadline | Evidence reference | Required? | Result | Notes or exceptions
T01 | Inventory URLs, templates, media and existing redirects |  | None |  |  | Yes | Not checked
T02 | Archive search, lead and performance baselines |  | T01 |  |  | Yes | Not checked
T03 | Approve keep, redirect and retire decisions |  | T01 |  |  | Yes | Not checked
T04 | Compare content, metadata and canonical signals |  | T03 |  |  | Yes | Not checked
T05 | Check images, alt text and downloadable files |  | T01 |  |  | Yes | Not checked
T06 | Check English/Lithuanian pairs and navigation |  | T04 |  |  | Yes | Not checked
T07 | Check old URLs and direct final redirect targets |  | T03 |  |  | Yes | Not checked
T08 | Check robots, noindex, sitemap and production access |  | T04; T06 |  |  | Yes | Not checked
T09 | Test English enquiry through to the right inbox |  | T04 |  |  | Yes | Not checked
T10 | Test Lithuanian enquiry through to the right inbox |  | T06 |  |  | Yes | Not checked
T11 | Test checkout or record why it does not apply |  | T01 |  |  | Yes | Not checked
T12 | Test consent and agreed analytics events |  | T09; T10 |  |  | Yes | Not checked
T13 | Test editor preview, publish and correction |  | T04 |  |  | Yes | Not checked
T14 | Rehearse recovery and confirm restore access |  | T01 |  |  | Yes | Not checked
T15 | Plan preservation of writes during cutover |  | T09; T10; T11 |  |  | Yes | Not checked
T16 | Assign immediate production checks and escalation |  | T07; T08; T12; T14; T15 |  |  | Yes | Not checked
Launch gates
ID | Acceptance gate | Owner | Depends on IDs | Deadline | Evidence reference | Required? | Result | Open condition
G01 | Baseline evidence archived and scope approved |  |  |  |  | Yes | Not checked
G02 | Every known URL has a reviewed decision |  |  |  |  | Yes | Not checked
G03 | Required customer journeys and language checks passed |  |  |  |  | Yes | Not checked
G04 | Recovery tested and rollback operator available |  |  |  |  | Yes | Not checked
G05 | Measurement definitions and evidence accepted |  |  |  |  | Yes | Not checked
G06 | Release owner accepts all required evidence |  |  |  |  | Yes | Not checked
Rollback actions
ID | Trigger and action | Decision or action owner | Prerequisite | When to act | Recovery evidence | Required? | Rehearsal result | Preserve new data
R01 | Wrong form recipient: restore previous frontend and retest delivery |  |  |  |  | Yes | Not checked
R02 | Key old URLs return 5xx: restore previous route config and retest |  |  |  |  | Yes | Not checked
R03 | Data restore: first reconcile new writes; obtain owner approval |  |  |  |  | Yes | Not checked
R04 | Rehearse rollback in staging and record restored customer flow |  |  |  |  | Yes | Not checked
Post-launch reviews
Day | Planned review | Review owner | Comparison dates or method | Search evidence | Lead/order evidence | Finding | Action owner and next step | Next review
7
14
28
Sources and use
S01 | Google site moves; reviewed 2026-10-28 |  | https://developers.google.com/search/docs/crawling-indexing/site-move-with-url-changes
S02 | Google hosting changes; reviewed 2026-10-28 |  | https://developers.google.com/search/docs/crawling-indexing/site-move-no-url-changes
S03 | Google redirects; reviewed 2026-10-28 |  | https://developers.google.com/search/docs/crawling-indexing/301-redirects
S04 | Web Aloha redirect mapper |  | https://webaloha.co/tools/seo-migration-redirect-mapper/
Evidence references must point to your own saved records. Do not enter passwords, personal enquiry details or customer payment data.

## URL template
Website migration URL register
Add one row per old URL. Keep/Redirect need a destination. Retire needs a reason and an intentional response.
ID | URL | Title | Language | Template | Inventory source | Decision | Destination URL | Reason | Template/URL owner | Dependency IDs | Expected source HTTP | Observed source HTTP | Expected canonical | Language pair ID | Evidence reference | Result | Row readiness

## Example plan
Fictional migration plan: Birch Studio / Beržo studija
Fictional people, dates and evidence. Reserved .example URLs. Open checks deliberately keep launch on hold.
Project | Birch Studio / Beržo studija (fictional)
Release owner | Mira, project owner (fictional)
Planned launch | 2026-11-04T12:00:00.000Z
Launch decision | Hold: baseline incomplete
Baseline evidence
ID | Measure | Scope or URL | Period or method | Evidence reference | Owner | Captured on | Result | Limits or notes
B01 | URL and redirect inventory | 8 old URLs; 7 destinations; EN and LT | Fictional crawl + CMS + media + redirects | SIMULATED B01: combined inventory | Mira, project owner | 2026-10-28T12:00:00.000Z | Pass | Teaching data; not a live crawl
B02 | Search Console export | Both language groups; web search | Final daily data; exact dates needed | Pending: daily export and coverage review | Jonas, search reviewer | 2026-10-28T12:00:00.000Z | Not checked | Unknown totals stay unknown, never zero
B03 | Enquiry/order baseline | English and Lithuanian enquiry inboxes | Count received enquiries separately from clicks | SIMULATED B03: inbox process reviewed | Mira, project owner | 2026-10-28T12:00:00.000Z | Pass | No real lead counts supplied
B04 | Representative speed test | Home + each service + contact template | Same page/device/tool settings before and after | SIMULATED B04: dated test settings | Ada, developer | 2026-10-28T12:00:00.000Z | Pass | No invented performance result
B05 | Platform and account inventory | Domain, DNS, host, repo, forms and analytics | Owner and recovery access inventory | SIMULATED B05: access register | Ada, developer | 2026-10-28T12:00:00.000Z | Pass | Do not store secrets in this workbook
B06 | Recovery point and restore test | Code release and external form storage | Staging rollback exercise | SIMULATED B06: recovery rehearsal | Ada, developer | 2026-10-28T12:00:00.000Z | Pass | Retain new inbox submissions
Task register
ID | Task and acceptance | Owner | Depends on IDs | Deadline | Evidence reference | Required? | Result | Notes or exceptions
T01 | Inventory URLs, templates, media and existing redirects | Ada, developer | None | 2026-11-02T12:00:00.000Z | SIMULATED T01: teaching acceptance reference | Yes | Pass | Fictional exercise; replace with actual evidence
T02 | Archive search, lead and performance baselines | Jonas, search reviewer | T01 | 2026-11-02T12:00:00.000Z | Pending: daily export | Yes | Not checked | Fictional exercise; replace with actual evidence
T03 | Approve keep, redirect and retire decisions | Jonas, search reviewer | T01 | 2026-11-02T12:00:00.000Z | SIMULATED T03: teaching acceptance reference | Yes | Pass | Fictional exercise; replace with actual evidence
T04 | Compare content, metadata and canonical signals | Ada, developer | T03 | 2026-11-02T12:00:00.000Z | SIMULATED T04: teaching acceptance reference | Yes | Pass | Fictional exercise; replace with actual evidence
T05 | Check images, alt text and downloadable files | Ada, developer | T01 | 2026-11-02T12:00:00.000Z | SIMULATED T05: teaching acceptance reference | Yes | Pass | Fictional exercise; replace with actual evidence
T06 | Check English/Lithuanian pairs and navigation | Jonas, search reviewer | T04 | 2026-11-02T12:00:00.000Z | SIMULATED T06: teaching acceptance reference | Yes | Pass | Fictional exercise; replace with actual evidence
T07 | Check old URLs and direct final redirect targets | Ada, developer | T03 | 2026-11-02T12:00:00.000Z | SIMULATED T07: teaching acceptance reference | Yes | Pass | Fictional exercise; replace with actual evidence
T08 | Check robots, noindex, sitemap and production access | Ada, developer | T04; T06 | 2026-11-02T12:00:00.000Z | SIMULATED T08: teaching acceptance reference | Yes | Pass | Fictional exercise; replace with actual evidence
T09 | Test English enquiry through to the right inbox | Mira, project owner | T04 | 2026-11-03T12:00:00.000Z | SIMULATED T09: teaching acceptance reference | Yes | Pass | Fictional exercise; replace with actual evidence
T10 | Test Lithuanian enquiry through to the right inbox | Mira, project owner | T06 | 2026-11-03T12:00:00.000Z | Pending: Lithuanian inbox receipt | Yes | Not checked | Form displays success; inbox delivery unknown
T11 | Test checkout or record why it does not apply | Ada, developer | T01 | 2026-11-03T12:00:00.000Z | SIMULATED T11: teaching acceptance reference | Yes | Not applicable | Service brochure; no store or payments
T12 | Test consent and agreed analytics events | Jonas, search reviewer | T09; T10 | 2026-11-03T12:00:00.000Z | Pending: consented event capture | Yes | Not checked | Fictional exercise; replace with actual evidence
T13 | Test editor preview, publish and correction | Ada, developer | T04 | 2026-11-03T12:00:00.000Z | SIMULATED T13: teaching acceptance reference | Yes | Pass | Fictional exercise; replace with actual evidence
T14 | Rehearse recovery and confirm restore access | Ada, developer | T01 | 2026-11-04T12:00:00.000Z | SIMULATED T14: teaching acceptance reference | Yes | Pass | Fictional exercise; replace with actual evidence
T15 | Plan preservation of writes during cutover | Ada, developer | T09; T10; T11 | 2026-11-04T12:00:00.000Z | SIMULATED T15: teaching acceptance reference | Yes | Pass | Fictional exercise; replace with actual evidence
T16 | Assign immediate production checks and escalation | Mira, project owner | T07; T08; T12; T14; T15 | 2026-11-04T12:00:00.000Z | SIMULATED T16: cutover operator and escalation assigned | Yes | Pass | Operator assigned now; production checks follow cutover
Launch gates
ID | Acceptance gate | Owner | Depends on IDs | Deadline | Evidence reference | Required? | Result | Open condition
G01 | Baseline evidence archived and scope approved | Mira, project owner | T01; T02 | 2026-11-04T12:00:00.000Z | Pending: prerequisite evidence | Yes | Not checked | Populated does not mean approved
G02 | Every known URL has a reviewed decision | Mira, project owner | T03; T07 | 2026-11-04T12:00:00.000Z | SIMULATED G02: teaching sign-off | Yes | Pass | Populated does not mean approved
G03 | Required customer journeys and language checks passed | Mira, project owner | T06; T09; T10; T11 | 2026-11-04T12:00:00.000Z | Pending: prerequisite evidence | Yes | Not checked | Populated does not mean approved
G04 | Recovery tested and rollback operator available | Ada, developer | T14; T15 | 2026-11-04T12:00:00.000Z | SIMULATED G04: teaching sign-off | Yes | Pass | Populated does not mean approved
G05 | Measurement definitions and evidence accepted | Mira, project owner | T02; T12 | 2026-11-04T12:00:00.000Z | Pending: prerequisite evidence | Yes | Not checked | Populated does not mean approved
G06 | Release owner accepts all required evidence | Mira, project owner | G01; G02; G03; G04; G05 | 2026-11-04T12:00:00.000Z | Pending: prerequisite evidence | Yes | Not checked | Populated does not mean approved
Rollback actions
ID | Trigger and action | Decision or action owner | Prerequisite | When to act | Recovery evidence | Required? | Rehearsal result | Preserve new data
R01 | Wrong form recipient: restore previous frontend and retest delivery | Ada, developer | Mira confirms wrong recipient; record incident | Immediately after confirmed failure | SIMULATED: prior deployment ID + form config | Yes | Pass | Preserve new inbox submissions; do not delete messages
R02 | Key old URLs return 5xx: restore previous route config and retest | Ada, developer | Jonas confirms affected priority URLs | At confirmed critical routing failure | SIMULATED: previous route config snapshot | Yes | Pass | Keep the reviewed URL map for repair
R03 | Data restore: first reconcile new writes; obtain owner approval | Mira, project owner | Identify every write since the restore point | Before any data restore | SIMULATED: external form-storage inventory | Yes | Pass | No website DB in this example; a store needs its own plan
R04 | Rehearse rollback in staging and record restored customer flow | Ada, developer | T14; named release access and recovery point | Before release approval | SIMULATED: restore rehearsal reference | Yes | Pass | A backup file alone is not a restore test
Post-launch reviews
Day | Planned review | Review owner | Comparison dates or method | Search evidence | Lead/order evidence | Finding | Action owner and next step | Next review
7 | 2026-11-11 12:00 | Jonas + Mira (fictional) | Use complete comparable windows; record other changes | Not yet collected; proposed launch is in future | Not yet collected | Unknown | Collect evidence after actual launch
14 | 2026-11-18 12:00 | Jonas + Mira (fictional) | Use complete comparable windows; record other changes | Not yet collected; proposed launch is in future | Not yet collected | Unknown | Collect evidence after actual launch
28 | 2026-12-02 12:00 | Jonas + Mira (fictional) | Use complete comparable windows; record other changes | Not yet collected; proposed launch is in future | Not yet collected | Unknown | Collect evidence after actual launch
Sources and use
S01 | Google site moves; reviewed 2026-10-28 |  | https://developers.google.com/search/docs/crawling-indexing/site-move-with-url-changes
S02 | Google hosting changes; reviewed 2026-10-28 |  | https://developers.google.com/search/docs/crawling-indexing/site-move-no-url-changes
S03 | Google redirects; reviewed 2026-10-28 |  | https://developers.google.com/search/docs/crawling-indexing/301-redirects
S04 | Web Aloha redirect mapper |  | https://webaloha.co/tools/seo-migration-redirect-mapper/
Evidence references must point to your own saved records. Do not enter passwords, personal enquiry details or customer payment data.
Formulas:
Measure = IF(ISNUMBER(B6),B6+[ID],"")

## Example URLs
Fictional bilingual URL register: Birch Studio / Beržo studija
Reserved .example URLs and simulated evidence. U06 stays open. These are not live HTTP observations.
ID | URL | Title | Language | Template | Inventory source | Decision | Destination URL | Reason | Template/URL owner | Dependency IDs | Expected source HTTP | Observed source HTTP | Expected canonical | Language pair ID | Evidence reference | Result | Row readiness
U01 | https://birch-studio.example/ | Birch Studio: website design | en | home | CMS + crawl | Keep | https://birch-studio.example/ | Same purpose and address | Ada | T04; T06 | 200 | 200 | https://birch-studio.example/ | home | SIMULATED U01: response and content review | Pass | Reviewed
U02 | https://birch-studio.example/lt/ | Beržo studija: svetainių kūrimas | lt | home | CMS + crawl | Keep | https://birch-studio.example/lt/ | Published Lithuanian homepage | Ada | T04; T06 | 200 | 200 | https://birch-studio.example/lt/ | home | SIMULATED U02: response and language review | Pass | Reviewed
U03 | https://birch-studio.example/services/web-design/ | Website design services | en | service | CMS + crawl + link targets | Redirect | https://birch-studio.example/website-design/ | Equivalent service at revised address | Jonas | T03; T07 | 301 | 301 | https://birch-studio.example/website-design/ | design | SIMULATED U03: direct redirect to 200 target | Pass | Reviewed
U04 | https://birch-studio.example/lt/paslaugos/svetaines/ | Svetainių kūrimo paslaugos | lt | service | CMS + crawl | Redirect | https://birch-studio.example/lt/svetainiu-kurimas/ | Equivalent Lithuanian service; retain language | Jonas | T03; T06; T07 | 301 | 301 | https://birch-studio.example/lt/svetainiu-kurimas/ | design | SIMULATED U04: redirect and pair review | Pass | Reviewed
U05 | https://birch-studio.example/contact/ | Contact Birch Studio | en | contact | CMS + crawl | Keep | https://birch-studio.example/contact/ | Existing contact address retained | Mira | T09 | 200 | 200 | https://birch-studio.example/contact/ | contact | SIMULATED U05: response and inbox test | Pass | Reviewed
U06 | https://birch-studio.example/lt/kontaktai/ | Susisiekite su Beržo studija | lt | contact | CMS + crawl | Keep | https://birch-studio.example/lt/kontaktai/ | Retain Lithuanian contact journey | Mira | T10 | 200 |  | https://birch-studio.example/lt/kontaktai/ | contact | Pending: public response and inbox receipt | Not checked | Needs review
U07 | https://birch-studio.example/uploads/services.pdf | Birch Studio service brochure | en | download | Media library + link targets | Redirect | https://birch-studio.example/downloads/services.pdf | Keep useful old file links working | Ada | T05; T07 | 301 | 301 | Not applicable: PDF redirect source | None | SIMULATED U07: file target and content review | Pass | Reviewed
U08 | https://birch-studio.example/lt/akcija-2024/ | Pasibaigusi 2024 metų akcija | lt | retired campaign | Historic redirect list | Retire |  | Expired offer; no relevant replacement | Mira | T03; T07 | 410 | 410 | Not applicable: retired | None | SIMULATED U08: intentional 410; links removed | Pass | Reviewed